## 루미르 발행문서
Last Updated: 2020-03-20
문서 번호 | 문서 제목 | 작성일 | Version | 파일이름 | 현황
KPLO-D1-554-012 | Declared Component List for SBC | 2019-12-20 | 3 | KPLO-D1-554-012 DCL_F3.0(20191220A)_200226서명본.pdf | 완료
KPLO-D1-554-016 | Declared Material List for SBC | 2018-10-15 | 1 | KPLO-D1-554-016 Declared Material List_ver1.0.pdf | 완료
KPLO-D1-554-022 | Declared Process List for SBC | 2018-10-15 | 1 | KPLO-D1-554-022 Declared Process List_ver 1.0.pdf | 완료
KPLO-D1-554-028 | KPLO-DTN Reliability Prediction Report | 2020-03-11 | F1.1 | KPLO-D1-554-028-F1.1 KPLO-DTN Reliability Prediction Report.docx | ETRI검토중
KPLO-D1-554-029 | DTN SBC Failure Mode, Effects, and Criticality Analysis | 2018-10-15 | 1 | KPLO-D1-554-029-F1.0 KPLO-DTN SBC_FMECA.DOCX.pdf | 검토중
KPLO-D1-554-032 | DTN SBC Part Stress Analysis | 2018-10-15 | 1 | KPLO-D1-554-032-F1.0 KPLO-DTN SBC_PSA.pdf | 완료
KPLO-D1-554-033 | DTN SBC Worst Case Analysis | 2018-10-15 | 1 | KPLO-D1-554-033-F1.0 KPLO-DTN SBC_WCA | 완료
KPLO-D0-550-007 | DTN Payload Test Procedure | 2020-01-16 | F1.0 | KPLO-D0-550-007-F.02 KPLO-DTN Test Procedure_200116B.docx | 업데이트 필요
KPLO-D0-550-100 | DTNPL Technical Description | 2018-10-29 | F1.0 | KPLO-D0-550-100-F1.0 KPLO-DTN Technical Description_181029A.DOCX | 완료
KPLO-D0-550-101 | DTNPL Mass Properties Report | 2018-10-29 | F1.0 | KPLO-D0-550-101-F1.0 KPLO-DTN Mass Properties Report_181029A.DOCX | 완료
KPLO-D0-550-102 | DTNPL Power Budget Analysis Report | 2018-10-29 | F1.0 | KPLO-D0-550-102-F1.0 KPLO-DTN Power Budget Analysis Report_181029A.DOCX | 업데이트 필요(실측값 반영)
KPLO-D0-550-103 | DTNPL Structural Analysis Report | 2017-12-28 | D.01 | KPLO-D0-550-103-D.01 KPLO-DTN Structural Analysis Report_171228A.docx | 업데이트 필요
KPLO-D0-550-104 | DTNPL Thermal Analysis Report | 2017-12-28 | D.01 | KPLO-D0-550-104-D.01 KPLO-DTN Thermal Analysis Report_171228A.docx | 업데이트 필요
KPLO-D0-550-200 | DTNPL Software Requirement Specification | 2017-12-28 | D.01 | KPLO-D0-550-200-D.01 KPLO-DTN Software Requirement Specification_171228A.docx | 업데이트 필요
KPLO-D0-550-201 | DTNPL Software Technical Description | 2017-12-28 | D.01 | KPLO-D0-550-201-D.01 KPLO-DTN Software Technical Description_171228A | 업데이트 필요
KPLO-D0-550-202 | DTNPL Software Test Plan & Procedures | 2017-12-28 | D.01 | KPLO-D0-550-202-D.01 KPLO-DTN Software Test Plan & Procedures_171228A.docx | 업데이트 필요
KPLO-D0-550-203 | DTNPL Software Test Results | 2017-12-28 | D.01 | KPLO-D0-550-203-D.01 KPLO-DTN Software Test Results_171228A.docx | 업데이트 필요
KPLO-D0-550-300 | DTNPL EGSE Specification | 2018-10-29 | F1.0 | KPLO-D0-550-300-F1.0 KPLO-DTN EGSE Specification_181029A.docx | 완료
KPLO-D0-550-301 | DTNPL EGSE Technical Description | 2017-12-28 | D.01 | KPLO-D0-550-301-D.01 KPLO-DTN EGSE Technical Description_171228A.docx | 업데이트 필요
KPLO-D0-550-440 | DTNPL Qualification Model EMI/EMC Test Procedure | 2019-03-01 | 1 | KPLO-D0-550-440_Ver 1.0 KPLO-DTN EMI_EMC Test 시험진행본_190429A.pdf | 완료
KPLO-D0-550-450 | DTNPL Qualification Model Thermal Cycling Test Procedure | 2019-02-19 | 1 | KPLO-D0-550-450_Ver 1.0_KPLO-DTN SBC QM Thermal Cycling Procedure_시험진행본_190429A.pdf | 완료
KPLO-D0-550-460 | DTNPL Qualfication Model Thermal Vacuum Test Procedure | 2019-03-12 | 1 | KPLO-D0-550-460_Ver 1.0 KPLO-DTN Thermal Vacuum Test Procedures_190429A.pdf | 완료
KPLO-D0-550-470 | DTNPL Qualification Model Vibration Test Procedure | 2019-03-11 | 1 | KPLO-D0-550-470_Ver 1.0 KPLO-DTN Vibration Test Procedure_시험진행본_190429A.pdf | 완료
KPLO-D0-550-480 | DTNPL Qualification Model Shock Test Procedure | 2019-03-28 | 1 | KPLO-D0-550-480_Ver 1.0 KPLO-DTN Shock Test Procedure_시험진행본_190429A.pdf | 완료
KPLO-D0-550-420 | DTNPL Flight Model EMI/EMC Test Procedure | 2020-04-23 | F.00 | DTNPL Flight Model EMI/EMC Test Procedure_200423A.docx | 완료
KPLO-D0-550-421 | DTNPL Flight Model Thermal Vacuum Test Procedure | 2020-04-23 | F.00 | DTNPL Flight Model Thermal Vacuum Test Procedure_200423A.docx | 완료
KPLO-D0-550-422 | DTNPL Flight Model Vibration Test Procedure | 2020-04-23 | F.00 | DTNPL Flight Model Vibration Test Procedure_200423A.docx | 완료
KPLO-D1-554-027 | Cleanroom Operation Procedure for DTN Payload | 2020-06-03 | F.00 | KPLO-D1-554-027-F.00 Cleanroom Operation Procedure for DTN Payload_200603A.docx | ETRI 송부

## Operation
DTN Operation 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정
[6 empty] | SDR | PDR | CDR | TRR | TRB
KPLO-D0-551-001 | Operation Concept | ETRI |  | 1 | O | Draft |  | Final
KPLO-D0-551-002 | Operation Scenario | ETRI |  | 0.1 | X | Draft |  | Final

## DTN test
DTN IOT 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정
[6 empty] | CDR | IRR
KPLO-D0-551-003 | DTN IOT plans | ETRI |  |  |  | Draft | Final
KPLO-D0-551-004 | DTN IOT procedures | ETRI |  |  |  | Draft | Final

## DTNPL
DTN Payload 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정 | [5 empty] | 비고
[6 empty] | SDR | PDR | CDR | TRR | PTR | Delivery
System Documents
KPLO-D0-550-000 | DTNPL System Requirements | ETRI |  | 2 | O | Draft | Final
KPLO-SP-550-001 | DTNPL System Specifications | ETRI |  | 1 | O | Draft | Final
KPLO-D0-550-002 | Interface Control Document | ETRI | Lumir | 1.43 |  |  | Draft | Final
DTNPL H/W Design
KPLO-D0-550-100 | DTNPL Technical Description | Lumir |  | F1.0 |  |  | Draft | Final |  |  |  | 완료
KPLO-D0-550-101 | Mass Properties Report | Lumir |  | F1.0 |  |  | Draft | Final |  |  |  | 완료
KPLO-D0-550-102 | Power Budget Analysis Report | Lumir |  | F1.0 |  |  | Draft | Final |  |  |  | 업데이트 필요(실측값 반영)
KPLO-D0-550-103 | Structural Analysis Report | Lumir |  | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
KPLO-D0-550-104 | Thermal Analysis Report | Lumir |  | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
DTNPL S/W Design
KPLO-D0-550-200 | DTN Software Requirement Specification (SRS) | Lumir | Lumir | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
KPLO-D0-550-201 | DTNPL S/W Technical Description | Lumir | ETRI | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
KPLO-D0-550-202 | DTNPL S/W Test Plan & Procedures | Lumir | ETRI | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
KPLO-D0-550-203 | DTNPL S/W Test Results | Lumir | ETRI | D.01 |  |  |  | Final |  |  |  | 업데이트 필요
EGSE Design
KPLO-D0-550-300 | EGSE Specifications | Lumir | ETRI | F1.0 |  |  | Draft | Final |  |  |  | 업데이트 필요
KPLO-D0-550-301 | EGSE Technical Description | Lumir |  | D.01 |  |  | Draft | Final |  |  |  | 업데이트 필요
DTNPL Verifications
KPLO-D0-550-005 | Verification Plans | ETRI |  | 1 | O |  | Draft | Final
KPLO-D0-550-006 | Test Plans | ETRI | Lumir | 1 |  |  |  | Draft | Final
KPLO-D0-550-007 | DTN Payload Test Procedure | Lumir | ETRI | F1.0 |  |  |  |  | Final |  |  | 업데이트 필요
KPLO-D0-550-008 | DTN Payload Test Results | Lumir | [7 empty] | Final |  | 작성필요
KPLO-D0-550-420 | DTNPL Flight Model EMI/EMC Test Procedure | Lumir | [6 empty] | Final |  |  | 작성필요
KPLO-D0-550-421 | DTNPL Flight Model Thermal Vacuum Test Procedure | Lumir | [7 empty] | Final |  | 작성필요
KPLO-D0-550-422 | DTNPL Flight Model Vibration Test Procedure | Lumir | [6 empty] | Final |  |  | 작성필요
KPLO-D0-550-440 | DTNPL Qualification Model EMI/EMC Test Procedure | Lumir |  | F1.0 |  |  |  | Draft | Final |  |  | 완료
KPLO-D0-550-450 | DTNPL Qualification Model Thermal Cycling Test Procedure | Lumir |  | F1.0 |  |  |  |  | Draft | Final |  | 완료
KPLO-D0-550-460 | DTNPL Qualification Model Thermal Vacuum Test Procedure | Lumir |  | F1.0 | [7 empty] | 완료
KPLO-D0-550-470 | DTNPL Qualification Model Vibration Test Procedure | Lumir |  | F1.0 | [7 empty] | 완료
KPLO-D0-550-480 | DTNPL Qualification Model Shock Test Procedure | Lumir |  | F1.0 | [7 empty] | 완료
Operation
KPLO-D0-550-500 | DTNPL Operation Handbook | Lumir | [8 empty] | Final | 작성필요
KPLO-D0-550-500 | EGSE Operation Handbook | Lumir | [8 empty] | Final | 작성필요

## PA
PA 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정 | [5 empty] | 비고
[6 empty] | SDR | PDR | CDR | TRR | TRB | Delivery
PA Plan Documents
KPLO-D0-554-001 | PAPP | ETRI |  |  |  | Draft | Final
KPLO-D0-554-002 | Configuration & Documentation Management Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-004 | EEE Parts Control Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-004 | Material & Process Control Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-005 | Contamination Control Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-006 | Safety Control Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-007 | Reliability Program Plan | ETRI |  | 1 | O | Draft | Final
KPLO-D0-554-008 | Subcontractor PAR | ETRI |  | 1 | O | Draft | Final
PA TM Documents
KPLO-D1-554-009 | Configuration Numbering Rule | ETRI | Lumir | 1 |  | Final
KPLO-D1-554-010 | Korean Industry capability check list form | ETRI | Lumir | 1 |  | Final
KPLO-D1-554-011 | DTN payload 개발 참여업체 Site survey 수행 계획(안) | ETRI | Lumir | 1 |  | Final
KPLO-D1-554-012 | Declared Component List for SBC | Lumir | ETRI | 3 | O |  | Draft | Final |  |  |  | 완료
KPLO-D1-554-013 | EEE parts Recertification Guideline | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-014 | Handling, Packing, Transportation, Unpacking, Installation & Storage | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-015 | Cleaning Procedure | Lumir | ETRI |  |  | Draft | Final |  |  |  |  | 완료
KPLO-D1-554-016 | Declared Material List | Lumir | ETRI | 1 | O |  | Draft | Final |  |  |  | 완료
KPLO-D1-554-017 | Shelf Life Material Control Procedure | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-018 | Safety Requirement | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-019 | ESD Control Plan | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-020 | Reliability Analysis Requirement | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-021 | EEE Parts Derating Guideline | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-022 | Declared Processes List | Lumir | ETRI | 1 | O |  | Draft | Final |  |  |  | 완료
KPLO-D1-554-023 | Product Assurance Board Plan | ETRI | Lumir | 1 |  | Final
KPLO-D1-554-024 | DTN payload Manufacturing Plan | ETRI | Lumir | 1 |  |  | Final
KPLO-D1-554-025 | Marking & Labeling Guideline | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-026 | DTN payload MRR check list | ETRI | Lumir | 1 |  | Draft | Final
KPLO-D1-554-027 | Cleanroom Operation Procedure for DTN Payload | Lumir | ETRI | F.00 |  | Draft | Final |  |  |  |  | 완료
KPLO-D1-554-028 | Reliability Analysis (Prediction/Assessment) | Lumir | ETRI | 1.1 |  |  | Draft | Final |  |  |  | 완료
KPLO-D1-554-029 | FMECA | Lumir | ETRI | 1 |  |  | Draft | Final |  |  |  | 완료
KPLO-D1-554-030 | Critical Item List | Lumir | ETRI |  |  |  | Draft | Final |  |  |  | 삭제 요청(Lumir) --> 삭제승인(ETRI)
KPLO-D1-554-031 | Single Point Item List | Lumir | ETRI |  |  |  | Draft | Final |  |  |  | 삭제 요청 (Lumir) --> 삭제승인(ETRI)

## DTNGS
DTN Ground Station 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정
[6 empty] | SDR | PDR | CDR | TRR | TRB
KPLO-D0-552-001 | DTNGS Requirements | ETRI |  | 1 | X | Draft | Final
KPLO-SP-552-002 | DTNGS Specifications | ETRI |  | 1 | X | Draft | Final
KPLO-D0-552-003 | DTNGS ICD | ETRI |  | D-02 | X |  | Draft | Final
KPLO-D0-552-004 | DTNGS Technical Description | ETRI |  |  |  |  | Draft | Final
KPLO-D0-552-005 | DTNGS Test Plans | ETRI |  |  |  |  | Draft | Final
KPLO-D0-552-006 | DTNGS Test Procedures | ETRI | [5 empty] | Draft | Final
KPLO-D0-552-007 | DTNGS Test Results | ETRI | [7 empty] | Final

## Proximity-1
Proximity-1 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정
[6 empty] | SDR | PDR | CDR | TRR | TRB | Launch
KPLO-D0-553-001 | Proximity-1 Requirements | ETRI |  | 1 | X | Draft | Final
KPLO-SP-553-002 | Proximity-1 Specifications | ETRI |  | 1 | X | Draft | Final
KPLO-D0-553-003 | Proximity-1 ICD | ETRI |  | D-02 | X |  | Draft | Final
Technical Description |  | ETRI |  |  |  |  | Draft | Final
KPLO-D0-553-100 | L2 S/W Technical Description | Cmax |  |  |  |  | Draft | Final
KPLO-D0-553-101 | PHY Technical Description | Wiznova |  |  |  |  | Draft | Final
KPLO-D0-553-102 | RF/IF Technical Description | Nimbus |  |  |  |  | Draft | Final
KPLO-D0-553-103 | Proximity-1 Technical Description | ETRI |  |  |  |  | Draft | Final
Test Plans & Procedures | [7 empty] | Draft | Final
KPLO-D0-553-200 | L2 S/W Test Plans & Procedures | Cmax | [5 empty] | Draft | Final
KPLO-D0-553-201 | PHY Test Plans & Procedures | Wiznova | [5 empty] | Draft | Final
KPLO-D0-553-202 | RF/IF RF/IF Test Plans & Procedures | Nimbus | [5 empty] | Draft | Final
KPLO-D0-553-203 | Proximity-1 Test Plans | ETRI | [5 empty] | Draft | Final
KPLO-D0-553-204 | Proximity-1 Test Procedures | ETRI | [5 empty] | Draft | Final
Test Results | [9 empty] | Final
KPLO-D0-553-300 | L2 S/W Test Results | Cmax | [7 empty] | Final
KPLO-D0-553-301 | PHY Test Results | Wiznova | [7 empty] | Final
KPLO-D0-553-302 | RF/IF Test Results | Nimbus | [7 empty] | Final
KPLO-D0-553-303 | Proximity-1 Test Results | ETRI | [7 empty] | Final
Operation
KPLO-D0-553-400 | Proximity-1 Operation Handbook | ETRI | [8 empty] | Final

## NASA test
ETRI-NASA DTN Test 문서
문서 번호 | 문서 제목 | 작성(정) | 작성(부) | 현황 | 서명 | 문서 일정
[6 empty] | 2016 | 2017 | 2018 | 2019 | 2020
Phase 1
KPLO-D0-555-000 | ETRO-NASA DTN Test Scenarios | ETRI | NASA | 1 | X | O
KPLO-D0-555-000 | Phase-1 Test Plans | ETRI | NASA
KPLO-D0-555-001 | Phase-1 Test Procedures | ETRI | NASA | 1 | X | O
KPLO-D0-555-002 | Phase-1 Test Summary | ETRI | NASA | PPT | X |  | O
Phase 2
KPLO-D0-555-100 | Phase-2 Test Plans | ETRI | NASA | PPT | X |  | O
KPLO-D0-555-101 | Phase-2 Test Procedures | ETRI | NASA | 0.1 | X |  | O
KPLO-D0-555-102 | Phase-2 Test Results | ETRI | NASA
Phase 3
KPLO-D0-555-200 | Phase-3 Test Plans | ETRI | NASA |  |  |  | O
KPLO-D0-555-201 | Phase-3 Test Procedures | ETRI | NASA |  |  |  | O
KPLO-D0-555-202 | Phase-3 Test Results | ETRI | NASA |  |  |  |  | O
Phase 4
KPLO-D0-555-300 | Phase-4 Test Plans | ETRI | NASA |  |  |  |  | O
KPLO-D0-555-301 | Phase-4 Test Procedures | ETRI | NASA |  |  |  |  | O
KPLO-D0-555-302 | Phase-4 Test Results | ETRI | NASA | [5 empty] | O